## Read Me
ABK Integration Team Tracker
ABK Integration Team tracker: projects, tasks (yours and the team's), team workload and a release log. Single source for the team's IBM ACE / MQ work.
How it fits together
Projects | One row per project. Task counts and % complete are calculated from the Tasks sheet by Project ID.
Tasks | One row per task, yours and the team's. Assigned To = the name in Lists!K4 marks a task as yours. Filter column F to see one person's list.
Team | One row per person. Open / blocked / overdue counts are calculated from Tasks. Add people here first so they appear in the Assigned To dropdown.
Releases | Append-only log of which BAR / version went to which environment. No formulas.
Dashboard | All formulas. Nothing to type. Shows projects by status and RAG, tasks by status split mine vs team, attention signals, team workload, project health.
Lists | Dropdown vocab and two settings: your name (K4) and the 'due soon' window in days (K5).
Colour legend
White cells | Type here. Dropdowns are enforced; edit the Lists sheet to add values.
Grey cells | Formulas. Do not overwrite. If you paste over one, copy it down again from a neighbouring row.
Yellow cells (Lists) | Settings you are expected to change.
Red / amber / green | Automatic: Overdue, Blocked, RAG, Critical priority, due-soon highlights.
Daily routine
1 | Open Dashboard. Anything red in 'Needs attention' is today's list.
2 | Update Status, Last Update and Blocker on the Tasks sheet. Set Completed when a task is Done.
3 | New task: add a row at the bottom of Tasks; give it the next TSK number and a Project ID from the dropdown. Formulas in C, L, M are pre-filled to row 504.
4 | Weekly: update RAG and Next Milestone on Projects.
Limits and assumptions
Capacity | Formulas cover 200 projects, 500 tasks, 50 team members, 500 releases. Copy the formula rows down to extend.
Sample data | Rows marked 'Sample row - replace' on Projects, Tasks, Team, Releases are placeholders showing the expected format. Delete them before real use.
Dates | Days Left and Overdue use TODAY(); they change every time the file is opened. Excel needs automatic calculation on (Formulas > Calculation Options).
Ownership | Assumes this workbook is the only tracker. If the team logs work in Jira / ServiceNow / ADO, keep only projects and milestones here or it will drift.
Effort | No estimated / actual hours by design. Add columns to Tasks if you need effort reporting.
Sharing | No sheet protection, so it can sit on SharePoint / OneDrive and be updated by the team. Grey columns are the ones to keep hands off.

## Dashboard
ABK Integration Team Dashboard
Everything on this sheet is calculated. Update Projects, Tasks and Team; this refreshes on recalc (F9 in Excel if calc is manual).
As of | 2026-09-14 |  | Tracking for | Phani
Projects by status |  |  |  |  | Tasks by status
Status | Count | Green | Amber | Red | Status | Mine | Team | Total | Overdue
Initiation | 1 | 1 | 0 | 0 | Not Started | 3 | 0 | 3 | 0
In Progress | 1 | 0 | 1 | 0 | In Progress | 1 | 3 | 4 | 0
On Hold | 1 | 0 | 0 | 1 | On Hold | 0 | 1 | 1 | 0
UAT | 1 | 1 | 0 | 0 | Blocked | 1 | 1 | 2 | 2
Go-Live | 0 | 0 | 0 | 0 | Done | 0 | 3 | 3 | 0
Closed | 0 | 0 | 0 | 0 | Cancelled | 0 | 0 | 0 | 0
Total | 4 | 2 | 1 | 1 | Total | 5 | 8 | 13 | 2
Needs attention |  |  |  |  | Team workload
Signal | Mine | Team | Total |  | Name | Open | In Progress | Blocked | Overdue
Overdue tasks | 1 | 1 | 2 |  | Phani | 5 | 1 | 1 | 1
Due within window (Lists!K5 days) | 3 | 1 | 4 |  | Ravi Kumar | 0 | 0 | 0 | 0
Blocked tasks | 1 | 1 | 2 |  | Priya Nair | 2 | 0 | 1 | 1
Open Critical / High tasks | 3 | 2 | 5 |  | Suresh Babu | 1 | 1 | 0 | 0
Open tasks with no due date | 0 | 0 | 0 |  | Anita Rao | 2 | 2 | 0 | 0
Open tasks with no owner |  | 0 | 0
Shows the first 10 rows of the Team sheet; see Team for the full list.
Project health (first 10 projects; see Projects sheet for all)
Project ID | Status | RAG | Open | Overdue | Project name | Lead | Target Go-Live | Days to Go-Live | % Complete
PRJ-001 | In Progress | Amber | 3 | 1 | SAP to Salesforce order sync (ACE 12) | Phani | 2026-10-19 | 35 | 25%
PRJ-002 | UAT | Green | 2 | 0 | ACE 12.0.12 fixpack rollout on AIX 7.3 | Phani | 2026-09-28 | 14 | 50%
PRJ-003 | Initiation | Green | 2 | 0 | MQ cluster consolidation (QM03/QM04) | Suresh Babu | 2026-12-13 | 90 | 0%
PRJ-004 | On Hold | Red | 2 | 1 | Payments REST API via NGINX gateway | Phani | 2026-11-13 | 60 | 0%
Formulas:
Green = COUNTIFS(Tasks!$H5:H504,"<>Done",Tasks!$H5:H504,"<>Cancelled",Tasks!$J5:J504,">="&TODAY(),Tasks!$J5:J504,"<="&TODAY()+Lists!$K5)-[Count]

## Projects
Projects
One row per project. Type in white cells; dropdowns come from the Lists sheet. Grey columns (K-O) are calculated from the Tasks sheet - do not overwrite.
Project ID | Project Name | Business Unit / Client | Type | Priority | Status | Lead | Start | Target Go-Live | RAG | Total Tasks | Done | Open | Overdue | % Complete | Next Milestone | Notes / Risks
PRJ-001 | SAP to Salesforce order sync (ACE 12) | Sales Ops | ACE Integration | High | In Progress | Phani | 2026-08-05 | 2026-10-19 | Amber | 4 | 1 | 3 | 1 | 25% | SIT sign-off | Sample row - replace. Salesforce sandbox refresh slipped one week.
PRJ-002 | ACE 12.0.12 fixpack rollout on AIX 7.3 | Platform | Upgrade / Fixpack | Critical | UAT | Phani | 2026-08-25 | 2026-09-28 | Green | 4 | 2 | 2 | 0 | 50% | PROD change window | Sample row - replace. CAB approval pending.
PRJ-003 | MQ cluster consolidation (QM03/QM04) | Platform | MQ | Medium | Initiation | Suresh Babu | 2026-09-09 | 2026-12-13 | Green | 2 | 0 | 2 | 0 | 0% | Design review | Sample row - replace.
PRJ-004 | Payments REST API via NGINX gateway | Finance | API Gateway | High | On Hold | Phani | 2026-07-16 | 2026-11-13 | Red | 2 | 0 | 2 | 1 | 0% | Security review | Sample row - replace. Blocked on client cert issuance from InfoSec.
Note on O4: Done / (Total - Cancelled). Blank until the project has at least one task.

## Tasks
Tasks (mine and the team's)
One row per task. Set Assigned To = your name (Lists!K4) for your own tasks; the Dashboard splits them from the team's. Grey columns C, L, M are formulas - do not overwrite. Filter by Assigned To to see one person's list.
Task ID | Project ID | Project Name | Task | Category | Assigned To | Priority | Status | Created | Due | Completed | Days Left | Overdue? | Blocker / Dependency | Last Update | Notes
TSK-001 | PRJ-001 | SAP to Salesforce order sync (ACE 12) | Review ESQL mapping for order header/line items | Review | Phani | High | In Progress | 2026-09-04 | 2026-09-16 |  | 2 |  |  | 2026-09-13 | Sample row - replace
TSK-002 | PRJ-001 | SAP to Salesforce order sync (ACE 12) | Build SAP IDoc DFDL model and ACE compute node | Build | Ravi Kumar | High | Done | 2026-08-15 | 2026-09-06 | 2026-09-05 |  |  |  | 2026-09-05
TSK-003 | PRJ-001 | SAP to Salesforce order sync (ACE 12) | Salesforce REST callout with OAuth policy | Build | Priya Nair | High | Blocked | 2026-08-30 | 2026-09-12 |  | -2 | OVERDUE | Waiting on Salesforce sandbox refresh | 2026-09-11
TSK-004 | PRJ-001 | SAP to Salesforce order sync (ACE 12) | SIT test cases for order sync happy path + retries | Testing | Anita Rao | Medium | In Progress | 2026-09-07 | 2026-09-24 |  | 10 |  |  | 2026-09-14
TSK-005 | PRJ-002 | ACE 12.0.12 fixpack rollout on AIX 7.3 | Backup nodes and BARs before fixpack apply | Deployment | Suresh Babu | Critical | Done | 2026-09-02 | 2026-09-09 | 2026-09-09 |  |  |  | 2026-09-09
TSK-006 | PRJ-002 | ACE 12.0.12 fixpack rollout on AIX 7.3 | Apply 12.0.12 fixpack on UAT integration nodes | Deployment | Ravi Kumar | Critical | Done | 2026-09-04 | 2026-09-11 | 2026-09-11 |  |  |  | 2026-09-11
TSK-007 | PRJ-002 | ACE 12.0.12 fixpack rollout on AIX 7.3 | Regression run on UAT after fixpack | Testing | Anita Rao | Critical | In Progress | 2026-09-11 | 2026-09-18 |  | 4 |  |  | 2026-09-14
TSK-008 | PRJ-002 | ACE 12.0.12 fixpack rollout on AIX 7.3 | Raise CAB change for PROD fixpack window | Governance | Phani | Critical | Not Started | 2026-09-12 | 2026-09-20 |  | 6
TSK-009 | PRJ-003 | MQ cluster consolidation (QM03/QM04) | Current-state MQ topology and channel inventory | Design | Suresh Babu | Medium | In Progress | 2026-09-09 | 2026-09-26 |  | 12 |  |  | 2026-09-13
TSK-010 | PRJ-003 | MQ cluster consolidation (QM03/QM04) | Consolidation design review with platform team | Meeting | Phani | Medium | Not Started | 2026-09-09 | 2026-10-04 |  | 20
TSK-011 | PRJ-004 | Payments REST API via NGINX gateway | Chase InfoSec for gateway client certificates | Governance | Phani | High | Blocked | 2026-08-15 | 2026-08-31 |  | -14 | OVERDUE | InfoSec ticket SEC-4412 open 3 weeks | 2026-09-07 | Escalate to InfoSec manager if no reply this week
TSK-012 | PRJ-004 | Payments REST API via NGINX gateway | NGINX upstream config for ACE HTTPS listener | Build | Priya Nair | Medium | On Hold | 2026-08-20 | 2026-10-14 |  | 30 |  | Depends on TSK-011 | 2026-09-07
TSK-013 |  |  | Monthly architecture governance forum - prep slides | Governance | Phani | Medium | Not Started | 2026-09-14 | 2026-09-19 |  | 5 |  |  |  | Non-project task: leave Project ID blank
Formulas:
Days Left = IF(OR([Due]="",[Status]="Done",[Status]="Cancelled"),"",[Due]-TODAY())
Overdue? = IF(AND([Due]<>"",[Status]<>"Done",[Status]<>"Cancelled",[Due]<TODAY()),"OVERDUE","")
Note on L4: Due - today. Negative = overdue. Blank once Done or Cancelled.
Note on M4: Shows OVERDUE when Due is in the past and status is not Done/Cancelled.

## Team
Team
Type in white cells (A-E). Grey columns are formulas pulled from the Tasks sheet - do not overwrite. Row 5 is you; keep your name identical to Lists!K4.
Name | Role | Primary Skills | Location / Shift | Notes | Open Tasks | In Progress | Blocked | Overdue | Done (all time)
Phani | Integration Architect | ACE 12, MQ, API design, governance | Onsite | Me | 5 | 1 | 1 | 1 | 0
Ravi Kumar | Senior ACE Developer | ESQL, JavaCompute, DFDL | Offshore | Sample row - replace | 0 | 0 | 0 | 0 | 2
Priya Nair | ACE Developer | ESQL, REST APIs, XMLNSC | Offshore | Sample row - replace | 2 | 0 | 1 | 1 | 0
Suresh Babu | MQ Administrator | MQ clusters, AIX, TLS | Onsite | Sample row - replace | 1 | 1 | 0 | 0 | 1
Anita Rao | Test Lead | SIT/UAT, SoapUI, Postman | Offshore | Sample row - replace | 2 | 2 | 0 | 0 | 0

## Releases
Release Log
Which BAR / version is in which environment. Append a row per deployment; newest at the bottom. Filter by Application + Environment to see what is live.
Date | Project ID | Application / BAR | Version | Environment | Node / Integration Server | Deployed By | Change Ref | Result | Notes
2026-09-05 | PRJ-001 | SAP_SFDC_OrderSync.bar | 1.3.0 | SIT | ACENODE01 / SIT_IS01 | Ravi Kumar | CHG0041220 | Success | Sample row - replace
2026-09-11 | PRJ-002 | ACE fixpack 12.0.12.0 | 12.0.12.0 | UAT | ACENODE02 / all servers | Ravi Kumar | CHG0041305 | Success | Sample row - replace
2026-09-13 | PRJ-001 | SAP_SFDC_OrderSync.bar | 1.3.1 | SIT | ACENODE01 / SIT_IS01 | Priya Nair | CHG0041331 | Failed | Sample row - replace. BIP2087E on deploy, policy project missing; redeployed 1.3.1 same day

## Lists
Dropdown values. Edit these to change the vocabulary used across the workbook. Do not insert columns.
Task Status | Priority | Project Status | Project Type | Task Category | Environment | RAG | Deploy Result | Setting | Value
Not Started | Critical | Initiation | ACE Integration | Design | DEV | Green | Success | My name (as used in Tasks > Assigned To) | Phani
In Progress | High | In Progress | MQ | Build | SIT | Amber | Failed | Dashboard 'due soon' window (days) | 7
On Hold | Medium | On Hold | API Gateway | Review | UAT | Red | Rolled Back
Blocked | Low | UAT | Upgrade / Fixpack | Testing | PRE-PROD
Done |  | Go-Live | BAU Support | Deployment | PROD
Cancelled |  | Closed |  | Governance
Meeting
Support